# Laying the Groundwork for Educational Master Planning

- Readiness for Change and Planning – Educational Master Plan due in May 2017

- Stakeholders

| - Internal stakeholders | - External stakeholders |
| --- | --- |
| - Cabinet - Councils - Departments - Divisions - Senates - District - Committees (Curriculum, Marketing, ACES) - Students | - Advisory groups - K-12 districts - Job train - Adult schools - Community partners - Business - Government agencies |

- Sponsor – Role is to Create the Plan

  - Create a Planning Team (10)

    - Tri-Chair: Dean of PRIE (1)

    - Tri-Chair: AS President (1)

    - Tri-Chair: Classified Senate President (1)

    - Faculty representatives (division, 4)

    - Classified staff (academic support and administrative service, 2)

    - Student representative (1)

    - President invited as a guest (VPs and Deans at times)

  - Define the Role of the planning team

  - Provide training for the team

  - Create a glossary of terms

  - Create a communication plan and timeline of activities with expected outcomes

- EMP Planning Team Timeline:

- May 2016: Planning Team charge, role, and responsibilities (PBC)

- June 2016: SCUP Planning Institute 1 Training

- July 2016: Outline Communication Plan and Planning Team Tasks

- August Flex: seeking feedback from the College

- August and September 2016: Seek feedback from all groups.

- September and October 2016: Seek feedback from all groups.

- November 2016: Starting to write the draft EMP

- January 2017: Draft EMP shared at FLEX Day and to PBC for feedback

- February through April 2017: Draft EMP to all groups for feedback

- May 2017: Final EMP to PBC for approval

- July 2017: Implementation of the EMP

- Plan may include the following:

- Environmental scan (District)

- Institutional context

- Competitor analysis

- SWOT (District)

- Mission, vision, values

- Strategic issues