## Slide 1: Success Team Pilot Evaluation
Discussion
Guided Pathways Steering Committee
May 18, 2021

## Slide 2: Success Team Pilot – Summary Findings
We have not implemented Success Teams as designed during this pilot. Possible factors:
  Success Team members were not clear of their roles (except Science and Health)
    IA faculty: not clear of their role; not clear on who was on their team(s)
    Retention Specialists:
      Staffing limitation of having one RS for three IA’s – perhaps not reasonable she attend all three SS meetings?
      COP an effective way to align RS services – what is it’s relationship to the IA Success Teams?
    Counselors: some not identified until well into the semester
    Data Coaches: not involved effectively in all IAs. Supported the COP of Retention Specialists with data.
  Success Teams did not meet regularly (except Science and Health)
  IA Faculty Leads and IA Deans were not clear about who should organize the Success Team meetings, what the agendas should be
  The role of faculty, deans, counselors and data coaches in case management is not clear
The difference between IA Groups and IA Success Teams is not clear
What should the role of Division meetings be as a way to conduct business and include more business for the IA Group
Role of Steering Committee
  How is it that Success Team members (esp those on the Steering Committee) did not understand their roles?
  How did we get to the end of the term without knowing Success Teams were not meeting?

## Slide 3: Success Teams: these aspects are mutually determining
What
Who
Why
How often meet
Notes: We began with a definition of Success Teams (an idea)
  Who, what, when, why
We stumbled on “who” and “what” and so “when” didn’t quite happen

## Slide 4: Tension Between GP Structures of Implementation
GP Steering Committee
Success Teams
Divisions
Interest Area Groups
Are Interest Area groups needed in implementing GP?
How are these four structures communicating and collaborating?
What can be done to make the collaboration more effective?

## Slide 5: Issues to resolve
Role of IA Groups
  Do we need them?
  What’s the role of the Divisions?
Success Team staffing and reliance on Retention Specialists
Monitoring – role of Steering Committee
  How could we be more effective at catching problems earlier?

## Slide 6: Supports Needed/Feedback
Interest Area Success Team Evaluation Form
Success Team Member | Planned Activities | Art, Design & Performance | Business | Human Behavior and Culture | Science & Health
Retention Specialist | Initial message bundles System of regular contact with students Coordination With special programs retention specialists Integration of BANNER, CRM & Canvas tools | Same as HBC | Same as HBC | Contact information of support services in CRM? Access and training for CRM. Not all Retention Specialists have license to use CRM Are Retention Specialists using Canvas? And how? | Same as HBC
Counselor | Interest Area specific ed. planning for students Document and report trends in IA ed. Planning to inform Program Mapper, Course Schedule, and student engagement efforts System for regular ed. Planning sessions with IA students | Success team needs to meet to plan; do students in this IA have commonalities in their SEPs that would make sense to discuss in a group planning session? Fashion already has planning sessions that are program specific and do not apply to the entire IA. | Need a mech. to connect stu. with IA counselor to ensure that all stu. in the IA have an ed. Plan. Need mech. to track stu. by major and to obtain data specific to each major in the IA. | Need more messaging to students to make them better aware of Counselors assigned to their IA. Should be a cooperative effort between Counselor and Instructional Faculty. Planning around major & career | Developed a montly student outreach and activity plan in collaboration with the retention specialist. Needs more guidance about the student groups (characteristics and size) that need to e served.
Data Coach | Provide bundles of student data for Success Team members to inform the various milestones related to student engagement, completion, and overall success. Regular maintenance and reporting of data for all IA student contacts from the point of application | Success team needs to meet to formulate questions. Are there problems common to programs in the ADP IA that are not common across the campus? | Provided data as needed to facilitate a discussion and formulate ST goals. | Regular check ins with the retention specialists and success team to make sure they are getting what they need. End-of-term check-in meeting to assess any needed iterative changes. | Participated regularly at the ST meetings. Provided data as needed to facilitate a discussion and help formulate Success Team (ST) goals. There are two data sources feeding the ST needs. Is there an overlap? Is there a more effective way to share data?
Success Team | Onboarding and Matriculation Retention and Persistence Completion of Educational Goals | Full ADP Success Team has not met. Success team needs to meet to formulate goals. Waiting for faculty input for breakout session. Faculty discussion needs to happen. | Need larger participation of I.A. & success team staff for sustainability. Funded or otherwise supported for long-term sustenance, so that it is spread out amongst larger set of participants. Need funding support for resources Suggestion: (1) In regular interactions, parity across all I.A.s for a common space for activities such as: Learning Center, Peer Mentoring (PM), etc. (2) I.A.-specific PM, in addition to general pool of PMs |  | Unevenly implemented outreach to incoming students. Not sure what a full implementation will look like. For this reason could not plan for new activities. Will be useful to have a bit more structure to be able to design the work of the Success Team more effectively. Expand ST activities to the health majors. Expand internship activities to health majors.

## Slide 7: Slides below from “What’s in a Success Team” approved September 2020

## Slide 8: GUIDED PATHWAYS STRUCTURE 2020 - 2021
STEERING COMMITTEE: responsible for scaling Guided Pathways through a multi-year strategic plan and providing resources for Interest Area Groups/Success Teams
INTEREST AREA GROUPS: Meets regularly with Interest Area faculty and staff to develop First-Year Experience program and Career Exploration component by Summer 2021, as well as optimizing the schedule and program maps for Interest Area students (prospective, new and returning).
SUCCESS TEAMS: operations team; frequent contact with Success Team members and interest area students with the goal to ensure every new student is connected, contacted, and feels a sense of belonging
Notes: Manuel

## Slide 9
An Interest Area is a group of academic degree and certificate programs that share common core required courses and which may be similar in terms of the career interests students may have.
Notes: MANUEL
- History of how the word developed at Leadership Retreat
Wanted a relationship and identity to understand how we are I
Term meant to invoke a positive image of becoming . . . A state of transformation

## Slide 10
A Success Team is a small group of college faculty, staff and administrators who monitor student-level data in the Interest Area (and build and manage relationships with each student in the Interest Area) to help each student with:
  Onboarding and matriculation
  Retention and persistence
  Completion of education goals
Notes: MANUEL
- History of how the word developed at Leadership Retreat
Wanted a relationship and identity to understand how we are I
Term meant to invoke a positive image of becoming . . . A state of transformation

## Slide 11: STEERING COMMITTEE 2020 - 2021
Co-Chairs (2)
Faculty Leads (4)
Deans (6)
Best Practices Reps (2)
Data Analyst (1)
Specialist Reps (1 - 2)
Student Reps (1 – 2)
Interest Area Groups 2020 - 2021
Leadership Team:
      Faculty Lead
      Program Services Coordinator
      Interest Area Dean
Larger Team:
      Interest Area Faculty
      Specialists
      Data Coach
Goals:
      FYE, Career Expl., Sched. Optimization, Program Mapper
_________________________
_________________________
Core Success Team:
      Retention Specialist
      Counselor
      Faculty Lead
      Data Coach
      Peer Mentor(s)
Additional Team Members:
      Program Services Coordinator
      Interest Area Dean
      Special Program Retention Specialists
Goal: ensure every student is contacted, connected and feels a sense of belonging
Success teams
2020 - 2021

## Slide 12: STEERING COMMITTEE 2020 - 2021
Co-Chairs (2)
Faculty Leads (4)
Deans (6)
Best Practices Reps (2)
Data Analyst (1)
Classified Reps (1 - 2)
Student Reps (1 – 2)
Interest Area Groups 2020 - 2021
Leadership Team:
      Interest Area Faculty Lead
      Interest Area Program Services Coordinator
      Interest Area Dean (ADP: Hyla, B: Hyla, HBC: James, SH: Ameer)
Larger Team:
      Interest Area Faculty
      Data Coach
      Special Program Specialists (invited via Interest Area PSC)
Goals:
      FYE launch by Summer 2021
      Career Exploration by Summer 2021
      Program Mapper and schedule optimization
_________________________

## Slide 13: Success team: retention specialist
Areas of Impact
Create channels for frequent and consistent communication to students (text, email, phone, etc.)
Daily maintenance of system for all interest area student contacts from point of application (CRM, Banner, Canvas, etc.)
Maintain regular contact with students for them to enter and stay on the Interest Area pathway

## Slide 14: Success team: retention specialist
Areas of Impact
Create channels for frequent and consistent communication to students (text, email, phone, etc.)
Daily maintenance of system for all interest area student contacts from point of application (CRM, Banner, Canvas, etc.)
Maintain regular contact with students for them to enter and stay on the Interest Area pathway
Approx. 10 - 20 hrs/week
Weekly Success Team Mtgs (16 hrs/sem)
Develop initial message bundles (text, email, Canvas posts, etc.) by need or event
Establish system for regular contact with students (could be one-on-one case mgmt. and could be group sessions by milestone)
Coordination with special program retention specialists (Promise, ESL, EOPS, etc.)
Integration of Banner, CRM, & Canvas tools to help students stay on the path

## Slide 15: Success team: counselor
Areas of Impact
Provide Interest Area specific educational planning for students within their Interest Area
Document and report trends in interest area educational planning to inform Program Mapper, Course Scheduled, and student engagement efforts
Develop system for regular educational planning sessions with all Interest Area students

## Slide 16: Success team: faculty lead
Areas of Impact
Document and report trends in interest area course planning, curriculum, and instruction to inform student engagement efforts with the Success Team
Develop system to connect Success Team trends and feedback to larger Interest Area planning, including Program Mapper maintenance and updates, as well as other IA faculty engagement

## Slide 17: Success team: data coach
Areas of Impact
Provide bundles of student data for Success Team members to inform the various milestones related to student engagement, completion, and overall success
Regular maintenance and reporting of data for all interest area student contacts from point of application

## Slide 18
Next Steps
Where are we with staffing the success teams?
    Counselors (Max)
    Retention Specialists (Manuel/Karen)
What should be my next steps?
    Communities of Practice Meeting
    Interest Area Leadership Team Meetings
Tuesday, October 6, 2020
Next Mtg:
Notes: MAUREEN