## Slide 1: Annual Plan
2019-20
Approved by PBC on August 30, 2019
Progress Report to PBC on May 6, 2020

## Slide 3: FOCUS THIS YEAR: Guided Pathways Strategic Priority Projects
Redesign College Processes
  Constituent Relationship Management (CRM) System Design and Implementation
Interest Areas, Program Maps, and Schedule Optimization
Redesign Academic Support & First Year Experience
Early College Experiences
Online Education
Career Exploration & Job Placement
Notes: Manuel

## Slide 4: Re-Design College Processes: CRM
Action Item | Progress
Streamline the matriculation process | CRM matriculation process “go live”: June 15, 2020 Matriculation messages to come from Interest Area Success Navigators and/or student support programs as of May 5, 2020 Students complete all matriculation steps during PEP as of April, 2020
Organize student “Success Teams” aligned with Interest Areas | In process: PBC approved the concept and possible staffing for Interest Area Success Teams on April 15, 2020. Implementation May, 2020 – May, 2021 Welcome Center staff assigned to Interest Areas May, 2020 Counselors assigned to Interest Areas for PEPS April, 2020 PEPs conducted in Interest Area SEPs as of April, 2020
Build data dashboards and train data coaches to support these efforts | Interest Area (draft) dashboards available here. As CRM evolves, Success Teams and PRIE will develop case management dashboards/systems May 2020 and ongoing
Scale the number of Peer Mentors aligned with Interest Areas and programs | The number of peer mentors will stay the same 2020-21. Scaling to occur 2021-23 pending funding.
Notes: Max

## Slide 5: Establish Interest Areas and Program Maps (implement Program Mapper)
Action Item | Progress
Create draft Interest Areas and Program Maps for faculty review and refinement August – Oct 2019 | Done. Maps complete and Program Mapper beta-test with Counselors scheduled for June, 2020 Official public launch on July 1, 2020
Division leads to review draft maps on August 13 | Done. GP Faculty Leads supported Division faculty in reviewing and working on their maps all year
Use program mapping to optimize the course schedule for student completion | Work included in new Strategic Enrollment Management Plan, to be implemented in 2020-21
All interest areas and program maps loaded into Program Mapper by October 31 (in time for Spring enrollment) | Done as of May, 2020. Beta-test: June, 2020 “Go-live” for students: July 2020
Notes: Carol

## Slide 6: Re-design Academic Support & First Year Experience programs aligned with Interest Areas
Action Item | Progress
Inventory “what is” in terms of academic supports and first year experience | Done, early fall 2019
Examine effectiveness and create a vision of what could be | Done, November 1, 2019
Create resource allocation to support new vision | On-going. Student Equity & Achievement Budget re-aligned to support embedded tutors.
Launch Writing Center, scale peer mentoring and EPIC supplemental instruction programs and integrate retention programs into larger academic support structure | Writing Center launched fall 2019. EPIC tutors expanded to AB705 co-req classes. Retention programs aligning with newly forming Interest Area Success Teams from May 2020 on.
First Year Experience: Develop curriculum to support. Align with COLTS CON, JAMS, Promise Scale peer mentoring and align with this and Success Teams Embed financial literacy Utilize a case management approach to tracking “touch points” – like Promise | First Year Experience: To be done by Interest Area planning teams in 2020-21 Counselors assigned to each Interest Area to facilitate first semester SEPs through PEPS Some COLTS CON, JAMS, and Promise activites to align with and support Interest Areas summer 2020 Peer mentors to align with Success Teams starting 2020-21 Financial literacy embedded in FYE: to do in 2020-21 Utilize case management approach: Success Teams to do this 2020-21
Notes: Manuel/Mary

## Slide 7: Expand opportunities for Early College experiences (dual enrollment; Middle College)
Action Item | Progress
Work with SUHSD to identify best ways to expand dual enrollment and Middle College opportunities for high school students | Director of High School Transitions and Dual Enrollment hired spring 2020. This work to begin to scale in 2020-21.
Notes: Manuel

## Slide 8: Create an equitable experience for Online Students to support student success
Action Item | Progress
As part of program mapping and schedule optimization process, determine which courses should be online to maximize student success and completion | This work began in 2019-20. Work had changed radically due to instruction moving 100% online due to the COVID-19 pandemic. This work will be part of the Strategic Enrollment Management Plan implementation 2020-23.
Notes: Manuel

## Slide 9: Develop Career Exploration & Job Placement opportunities for students that are aligned and integrated with Interest Areas
Action Item | Progress
An inventory of what IS now (coop, STEM, Sparkpoint) | Done as fall 2019
Identify Holland Code(s) for every program on campus | In process of adopting MyMajors and integrating with Salesforce to help with career exploration/linkage with college programs. Implementation scheduled go-live for summer 2020.
Change Orientation to embrace Holland Codes and embed career exploration | 
Build systems for managing and scaling (Salesforce)? | 
Look at the role of career exploration counseling classes | MWF CRER 137 course developed for Promise, go live fall 2020
Leverage industry relationships and employer outreach activities | Spring 2020 job fair aligned with interest areas
Align with Outreach in general | Potential MyMajors collaboration opportunity summer 2020 and beyond
Scale career mentors and train them on career exploration tools | ?
Establish support networks aligned with Interest Areas | ?
Look at STEM Center Job Shadowing program and possibly scale | ?
Create an awareness brochure | ?
Make better use of LinkedIn | ?

## Slide 10: Looking ahead:
Implement the approved recommendations from the PBC Task Force on Participatory Governance Committee Structure, Roles, and Composition