## Slide 1: Capital Improvement Program Phase 3(CIP3)
APRIL 19, 2017 CAñada college CIP3 update forum

## Slide 2: Agenda
CIP3 Planning Efforts
Program Budget Overview
Program Overview
  Cañada College Building 1N
  Cañada College Building 23N
  Cañada College other projects
Tentative Schedule and Logistics
Q & A

## Slide 3: CIP3 Planning Efforts
Scheduling Consultant – Contract Awarded to AECOM (April 2015)
Cost Estimating Consultant – Contract Awarded to Leland Saylor Associates (April 2015)
California Environmental Quality Act (CEQA) – Completed (Winter 2015)
Construction Management (PM/CM) – Contract Awarded to Swinerton (March 2015)
Design Standards Revision – Completed (June 2015)
Swing Space Planning (ONUMA) – In Progress
Architect and Engineer (A&E) Selection for Design of First Wave Projects – Completed (April 2015)
Design Build Entity Selection (CAN B1N, SKY B12N, CAN B23N, SKY1N) – Complete
Design Build Entity Selection – In Progress (CSM Solar)
2017 Annual General Contractor and Major Subcontractor Prequalification Process – Complete
Project Labor Stabilization Agreement – Amendment Approved by BOT (March 2016), Execution in Process

## Slide 4: Project Budget Overview

## Slide 5: Cañada College
Project | Recommended Project Budget
Kinesiology and Wellness (B1N) | $108,000,000
Math Science Technology (B23N) | $55,800,000
Library and LRC Reconfiguration (B9) | $1,500,000
ADA Access Compliance (Ramp Upgrades) | $660,000
Central Plant Upgrade (B3) | $2,000,000
B16 & 18 Secondary Effects | $3,000,000
Multiple Program instruction Center FPP (B13) | $12,800,000
Total: | $183,760,000
Notes: Recommendations
B5 $9M / $4.5M Savings $4.5M

## Slide 6: Project Program Overview

## Slide 7: Cañada College Kinesiology & Wellness Building (B1N)
  Budget $108,000,000
    Measure H
  Project Scope
    Demolish existing Gymnasium and Construct a new 85,000 GSF Kinesiology & Wellness Building (B1N)
    The new building is a two story structure including a roof activated with athletic programs. It will house both academic and enterprise facilities, including classrooms for wellness activities, an extensive fitness center to serve both instructional and member uses, a NCAA competition basketball and volleyball gymnasium, locker and shower facilities, offices and auxiliary facilities. To the east of the building will be a competition pool and an instructional wellness pool. Parking Lot 6 will be expanded by 335 spaces and Parking Lot 4 will be replaced with a South Quad landscape area as the tie in to the new building
  Status
    Design Build Entity Blach Construction / ELS Architects is currently in Design Development Phase.
    Construction documents for Increment 1 site work will be submitted to DSA August 1, 2017
    Construction documents for Increment 2 building will be submitted to DSA December 1, 2017
  Tentative Construction Schedule
    Vacate existing B1 Summer 2017
    Salvage building equipment Summer 2017
    Utilities and hook up for Team Rooms 1 & 2 Summer 2017
    Construction fencing to be installed in August, 2017
    Hazardous materials abatement Fall 2017
    Building demolition Spring 2018
    Target occupancy Q2 2020

## Slide 8: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 9: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 10: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 11: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 12: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 13: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 14: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 15: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 16: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 17: Cañada College Kinesiology & Wellness Building (B1N)

## Slide 18: Cañada College Math Science Technology Building (B23N)
  Budget $55,800,000
    Measure H
  Project Scope
    Demolition of portion of hillside and “hump” of dirt between B22 & B18; spoils to be relocated to Lot 10
    Retaining wall and site preparation work to begin March 2018
    Construct new ~50,000 SF Math and Physical Science Building (B23)
    Elements of the program: New Science labs and Classroom Instruction space for Biology, Anatomy, Earth Science, Rad Tech, Computer Science, Astronomy; Includes 60-student capacity instruction spaces and office spaces
  Status
    McCarthy / HGA awarded design-build contract January 2017; Initial Programming complete; Schematic Design Phase to complete end of April 2017
    Design Document development end May 2017 – End September 2017; Construction Documents September – December 2017
  Tentative Construction Schedule
    Excavate and relocate dirt March 2018; Construction of building to begin July 2018
    Target occupancy Q1 2020

## Slide 19
Cañada College Math Science Technology Building (B23N)
PERSPECTIVE VIEW
SCHEME 2 - VIEW FROM PLAZA
                                

## Slide 20
Cañada College Math Science Technology Building (B23N)
PERSPECTIVE VIEW
SCHEME 2 - GROUND VIEW FROM SW
                                

## Slide 21
Cañada College Math Science Technology Building (B23N)
PERSPECTIVE VIEW
SCHEME 2 - VIEW FROM SW
                                

## Slide 22
0
Cañada College Math Science Technology Building (B23N)
PERSPECTIVE VIEW
SCHEME 2 - VIEW FROM NW
                                

## Slide 23
Cañada College Math Science Technology Building (B23N)
PERSPECTIVE VIEW
SCHEME 2 - VIEW FROM NE
                                

## Slide 24
Cañada College Math Science Technology Building (B23N)
PERSPECTIVE VIEW
SCHEME 2 - VIEW FROM SE
                                

## Slide 25
UP
UP




































DEPARTMENT LEGEND
  
  
  

















                                
3950-003-00
LEVEL 01
CAÑADA COLLEGE MATH, SCIENCE AND TECHNOLOGY CENTER
1" = 20'-0"

## Slide 26
UP
UP
DN


























DN 


DEPARTMENT LEGEND
   
 
 

  
 
 






 








                                
3950-003-00
LEVEL 02
CAÑADA COLLEGE MATH, SCIENCE AND TECHNOLOGY CENTER
1" = 20'-0"

## Slide 27
DN
DN











 
 



















DEPARTMENT LEGEND
 
  
 




3950-003-00
LEVEL 03
CAÑADA COLLEGE MATH, SCIENCE AND TECHNOLOGY CENTER
                                
1" = 20'-0"

## Slide 28: Cañada College Tentative Schedule
Schedule is subject to change due to agency requirements, unforeseen conditions, and/or design build contractor input

## Slide 29: Logistics

## Slide 30: Questions and Answers