Guided Pathways Exploration

Cañada College

Work Plan for 2017-2019

Team: 	See Excel Worksheet

Next Outcome:	Completed Workplan to the state by March 31, 2018

Three-Part Plan

The College will undertake an exploratory process in this upcoming year related to the following three areas:

- Student Voices

- Business Systems Analysis and Exploration of Services

  - Including Designing Sequence of Steps

  - Integration of Student and Academic Services

- Meta Majors and Designated Course Sequencing

The outcome in Spring of 2019 should be a clarified set of next steps to continue the remaining four years of our plan to:

- Redesign of systems for students that is responsive to their need for seamless services.

- Attends to pathways to lead to developmental readiness, transfer, or jobs.

- Clarity around academic pathways to ensure no excess credits or excess costs are incurred.

| Task | Including/Partner | Person | Begin Date | End Date |
| --- | --- | --- | --- | --- |
| Identify Populations | Returning, Exit Surveys (Alumni), First Time, Promise, Part-time, in community, commuter, concurrent, etc | Lead | Jul-18 | Aug-18 |
| Design Inquiry | Qualitative, Focus Groups, Survey Data | Lead and GPT Team | Jul-18 | Aug-18 |
| Identify Room | Business Office | Lead | Jul-18 |  |
| Identify Technology | Business Office | Lead | Jul-18 | Aug-18 |
| Outreach and Communication to To Campus | Marketing | Lead | Jun-18 | Continuous |
| Design Inquiry Process | Consultant | Lead | Jun-18 | Jul-18 |
| Identify Student Participants | ASCC | Lead | Jun-18 | Continuous |
| Focus Group #1 | Consultant | Lead w/Consultant | Sep-18 |  |
| Student Videos | Students | Contract/Students | Sep-18 | Oct-18 |
| Deliver Results | IT/Marketing | Lead | Oct-18 |  |
| Results to the Campus | Marketing/GPT | Lead | Oct-18 |  |
| Mini Campus Forum | Cabinet | GP Team | Oct-18 |  |
| Data back to GPT | Lead | Lead+B9:C14 | Oct-18 |  |
| Focus Group #2 | Consultant | Lead w/Consultant | Nov-18 |  |
| Student Videos | Students | Contract/Students | Nov-18 |  |
| Deliver Results | IT/Marketing | Lead | Nov-18 |  |
| Results to the Campus | Marketing/GPT | Lead | Nov-18 |  |
| Mini Campus Forum | Cabinet | GP Team | Nov-18 |  |
| Data back to GPT | Lead | Lead+B9:C14 | Nov-18 |  |
| Focus Group #3 | Consultant | Lead w/Consultant | Feb-19 |  |
| Student Videos | Students | Contract/Students | Feb-19 |  |
| Deliver Results | IT/Marketing | Lead | Feb-19 |  |
| Results to the Campus | Marketing/GPT | Lead | Feb-19 |  |
| Mini Campus Forum | Cabinet | GP Team | Feb-19 |  |
| Data back to GPT | Lead | Lead+B9:C14 | Feb-19 |  |
| culiminating Data informs campus | Cabinet | Lead/GPT | May-19 |  |
| Incorporate Into Year 2 | Cabinet | Lead/GPT | Jun-19 |  |

Student Voices

Business Systems Analysis and Exploration of Services

| Task | Including/Partner | Person | Process | Begin Date | End Date |
| --- | --- | --- | --- | --- | --- |
| Read and Review Guided Pathways | GPTF | Lead | COP | Sep-18 | Apr-19 |
| EAP Consultant | GPTF | VPSS |  | Feb-18 | Apr-18 |
| Communication Consultant | GPTF | Lead/VPSS |  | Mar-18 | Sep-18 |
| Lean/Six Sigma Training | GPTF/C. Senate | Lead/VPSS |  | Summer 2018 |  |
| Business Process Analysis | SSLT/VPA | Lead |  | Fall 2018 |  |
| Student Input and Feedback | ASCC | Lead |  | Fall 2018 |  |
| Communication with Cabinet | GPTF | Lead |  | Oct-18 | 18-Nov |
| Incorporate Changes | GPTF/VPA | Lead |  | End Fall 2018 |  |
| Request Changes through PBC | GPTF | Lead |  | Nov-18 | Mar-19 |
| Practice Changes | GPTF/VPSS | Lead |  | Spring 2019 |  |
| Assess for Effectiveness | GPTF/VPSS | Lead |  | Spring 2019 |  |
| Business Process Analysis #2 | SSLT/VPA | Lead |  | Spring 2020 |  |
| Student Input and Feedback #2 | ASCC | Lead |  | Spring 2021 |  |
| Communication with Cabinet #3 | GPTF | Lead |  | Mar-19 | 1-Jun |

| Task | Including/Partner | Person | Process | Begin Date | End Date |
| --- | --- | --- | --- | --- | --- |
| Team Convening | A. Senate | Lead |  | Jun-18 |  |
| Read and Review Guided Pathways | GPTF | Lead | COP | Sep-18 | Apr-19 |
| Visits | GPTF | Lead |  | Sep-18 |  |
| Data Inquiry | GPTF | Lead |  | Sep-18 |  |
| Assessment Review | GPTF | Lead |  | Oct-18 |  |
| Career Exploration | GPTF | Lead |  | Oct-18 |  |
| Employer/Transfer Feedback | GPTF | Lead |  | Oct-18 |  |
| First Meta Major Review | GPTF | Lead |  | Nov-18 |  |
| College Convening | GPTF | Lead |  | Dec-18 |  |
| Review and Incorporate Feedback | GPTF | Lead |  | Jan-19 |  |
| Visits | GPTF | Lead |  | Feb-19 |  |
| Data Inquiry | GPTF | Lead |  | Mar-19 |  |
| Assessment Review | GPTF | Lead |  | Apr-19 |  |
| Career Exploration | GPTF | Lead |  | Oct-18 |  |
| Employer/Transfer Feedback | GPTF | Lead |  | Oct-18 |  |
| Second Meta Major Review | GPTF | Lead |  | May-19 |  |
| College Convening | GPTF | Lead |  | Jun-19 |  |
| Recommendations for year 2 | Cabinet | Lead |  | Jun-19 |  |

Meta Majors and Designated Course Sequencing

This will be a faculty lead process that discovers appropriate pathways through speakers (visiting Cañada, visits to other colleges, readings, and a review of our student data.

Team

| Original Training Member | Team | Area |
| --- | --- | --- |
|  | James Carranza | Humanities & Social Sciences |
|  | Margie Carrington | FA |
| XX | Gloria Darafshi | Counseling |
|  | Daryan Chan | Counseling |
| XX | Denise Erickson | Humanities & Social Sciences |
|  | Robert Haick | Career Exploration |
| XX | Nenaji Jackson | ESO/Grants |
| XX | Alex Kramer | CTE/Workforce |
| XX | Ruth Miller | Admissions |
|  | Candice Nance | Business |
|  | Marisol Quevedo | Promise |
| XX | David Reed | ASLT |
|  | Jeanne Stalker | C. Senate |
|  | Rebekah Taveau | ESL |
|  | Maureen Wiley | English |
|  | Max Hartman | Counseling |
| XX | Phillip King | VPSS |
|  | Maria Huning | Trio |
|  | Dayo Diggs | Operations/Research |
| Recommended |  |  |
|  | Michael Hoffman | Math |
|  | Several Science Faculty | Science |
|  | Business Office |  |
|  | Janette Linares | CWA Counselor |
|  | Students |  |
| CLP Consultants |  |  |
|  | Katherine |  |
|  | Sima |  |
|  | Mina |  |
|  | Chase |  |