## Sheet1
Cañada College DRAFT Annual Plan: 2019-20
EMP Goal | EMP Strategic Initiative | Projects | Responsible Party | Work Group Members (required) | Expected Completion Date | Monitoring Planning Council
Student Success: Help students meet their academic goals |  | Create Interest Areas | VPSS | Maureen Wiley, Adam Windham, James Carranza, GP Faculty Coordinators | October, 2019 | IPC
|  | Create Program Maps | VPSS | Maureen Wiley, Chris Rico, Adam Windham, James Carranza |  | IPC
|  | Optimize course schedule for program completion | VPI | Office of INstruction |  | IPC
|  | Ensure all students have up-to-date Student Education Plans | VPSS | Max Hartman |  | SSPC
|  | Explore feasibility of blocking course sections for co-horts | VPI | Jose Pena, Instructional Deans |  | IPC
|  | Align role of Retention Specialists across campus | Dean of ASLT | Max Hartman and all other Deans |  | SSPC
|  | Expand Peer Mentorship Program | Dean of ASLT | Max Hartman and all other Deans |  | SSPC
|  | Expand access to financial aid | VPSS | Financial Aid Director |  | SSPC
|  | Expand access to book vouchers and OER/ZTC | VPSS | Jai Kumar |  | SSPC
|  | Expand access to transportation | VPSS |  |  | SSPC
|  | Continue monthly incentives to Promise Scholars | VPSS |  |  | SSPC
|  | Expand and improve access to supplemental instruction | Dean of ASLT | Max Hartman and all other Deans |  | IPC
|  | Scale access to CRER 137 | Max Hartman | Chris Rico |  | IPC
|  | Enable more students to meet with a career counselor regularly | Max Hartman | Chris Rico |  | SSPC
|  | Embed career exploration into course curricula aligned to Interest Areas | VPI |  |  | IPC
|  | Establish LinkedIn as career development tool for all students | VPI | Leonor Cabrera |  | SSPC
|  | Explore digital badging | VPI |  |  | IPC
|  | Complete re-branding of Career Education Programs | Leonor Cabrera |  |  | APC
|  | Integrate Career Center activities with CE and STEM Center career exploration and early career experience efforts | Julian Branch |  |  | SSPC
|  | Integrate Career Center activities with CE and STEM Center career exploration and early career experience efforts | Julian Branch |  |  | SSPC
|  | Complete design phase of CRM | Max Hartman |  |  | SSPC
|  | Establish First Year Experience Programs aligned with Interest Areas | VPSS |  |  | IPC
|  | Establish "Success Teams" aligned with Interest Areas | VPSS |  |  | SSPC
|  | Expand and improve access to supplemental instruction |  |  |  | SSPC
|  | Ensure access to student service for all student types/needs (e.g., am, pm, Saturday, etc) |  |  |  | SSPC
|  | Address faculty and student technology needs at each off-campus location |  |  |  | APC
|  | Improve access to technology and learning tools for all students |  |  |  | APC
|  | Develop 3-year plan for growing College for Working Adults |  |  |  | IPC
|  | Be more strategic in online course offerings |  |  |  | IPC
|  | Support strategies identified in program review |  |  |  | IPC
Community Connections: Strengthen community partnerships to support students and the local community |  | Increase high school dual enrollment opportunities | VPI |  |  | IPC
|  | Increase concurrent enrollment | VPI |  |  | IPC
|  | Expand Middle College | VPI |  |  | IPC
|  | Increase college and career exploration opportunities for student from feeder high schools | VPI |  |  | IPC
|  | Provide intentional support for AB 540 students | VPSS |  |  | SSPC
|  | Increase enrollment in off-campus ESL classes | VPI |  |  | IPC
|  | Align and coordinate outreach and community engagement activities | College Recruiter | Community Relations and Outreach |  | APC
|  | Host alumni as speakers | Community Relations | Workforce Director, STEM Center, ACES, Outreach |  | APC
|  | Connect with all alumni via LinkedIn | Community Relations | Workforce Director, STEM Center, ACES, Outreach |  | APC
|  | Tap alumni as possible job shadow or internship hosts | Community Relations | Workforce Director, STEM Center, ACES, Outreach |  | APC
|  | Strengthen the President's Annual Luncheon | Community Relations | Outreach |  | APC
|  | Strengthen Connect to College | Outreach/College Recruiter |  |  | APC
|  | Continue and align STEM and Equity Lecture Series | STEM Center and ACES | Community Relations and Outreach |  | IPC
|  | Strengthen Awareness Summit | Community Relations | Awareness Summit Committee |  | APC
|  | Re-launch the University Center | VPSS |  |  | SSPC
|  | Support connection between Career Education Programs and CSU partner programs | VPA | VPI, Dean of BDW, Digital Art Faculty |  | IPC
|  | Expand offerings in downtown location(s) | Director of Workforce Developemnt |  |  | IPC
Organizational Development: Focus institutional resources on transformative learning |  | Implement Professional Learning Plan |  |  |  | PBC
|  | Strengthen CIETL |  |  |  | PBC
|  | Strengthen and focus ACES |  |  |  | PBC
|  | Scale and require professional development for faculty teaching online |  |  |  | IPC
|  | Scale access to Net Tutor |  |  |  | SSPC
|  | Adopt Proctorio |  |  |  | IPC
|  | Enable CRM to integrate with Online Video Counseling | Max Hartman |  |  | SSPC
|  | Scale use of Screencast-o-Matic by faculty teaching online |  |  |  | IPC
|  | Develop and implement a fundraising strategy |  |  |  | APC
|  | Evaluate success of students as a result of AB 705 implementation | Max Hartman; PRIE
Identify additional support to grow KAD programs