## EMP
EMP Goal 1 Strategic Initiatives | EMP Goal 2 Strategic Initiatives | EMP Goal 3 Strategic Initiatives
1. Develop academic pathways and provide integrated support services that begin in high school, transition to college and complete with a certificate, degree and/or transfer. | 1. Collaborate with Pre-K to Adult School partners to promote relationships, seamless transitions, and alignment of pathways. | 1. Implement the Professional Learning Plan and establish a robust college-wide professional learning program that engages campus constituents while creating opportunities for innovative practices that support student success and promote equity.
2. Improve completion by developing and implementing a comprehensive college-wide approach to enrollment management, student retention, and course scheduling. | 2. Develop and support student internships, service learning opportunities, mentorships to improve connection of students to local organizations and employers. | 2. Implement Guided Pathways-like design principles to help address equity gaps.
3. Develop and implement a 2-pronged Promise Program to address ‘scholarship and academic support’ in addition to ‘personal student financial support’ to minimize the barriers caused by enrollment fees, cost of textbooks, parking fees, transportation, child care, food and housing insecurity. | 3. Attract the community to the campus through high profile signature events. | 3. Create robust processes and support for developing new academic programs/curricula including innovations that address geographic and logistic barriers to access.
4. Expand and extend cohort bridge programs to students beyond their first year of study. | 4. Create a Cañada College alumni organization to promote success stories, to engage successful community members, and to explore development opportunities. | 4. Identify and implement enrollment strategies and integrated planning and resource allocation processes to meet institutional and student success outcomes.
| 5. Establish structures and resources to initiate and build relationships with local businesses and industries for developing institutional partnerships. | 5. Promote a campus culture that fosters a climate of inclusivity.
| 6. Expand and enhance marketing of transfer and career technical education (CTE) opportunities. | 6. Institutionalize effective structures and best practices of HSI (Hispanic-Serving Institutions) and AANAPISI (Asian American and Native American Pacific Islander-Serving Institutions) in order to reduce the achievement gap.
| 7. Enhance and invest in 2+2 relationships with 4-year universities. | 7. Revise the college’s component of the Facilities Master Plan to identify and address space and facilities needs that arise out of implementing this 2017-2022 EMP.

## Progress on Goal 1
Goal 1: Student Completion Desired Outcomes | Action Steps to be Implemented in 2018-19 | Timeline | Responsible Parties | Planning Council Lead | Outcomes | Resources | Progress made in 2018-19
Clarify Academic Pathways | Explore whether creating meta majors (interest areas) would improve student outcomes | AY 2018-19 | Maureen Wiley, Denise Erickson | IPC | Decision on whether or not to establish meta majors for Canada | Guided Pathways Meta Major Working Group | Complete. Interest Areas are being defined.
| Evaluate the course schedule with respect to time-to-completion for the top 20 degree and certificate programs | AY 2018-19 |  | IPC |  |  | Not done
| Enhance and expand distance education strategically | AY 2018-19 | Lezlee Ware | IPC | Consider baseline data and decide where to grow based on student outcomes | DEAC | Process for determining which courses will be offered online was documented. Enhancing the quality of on-line instruction is on-going. DEAC has recommendations that need approval.
Identify and address business process barriers | Scale the Promise Program and evaluate Promise student experiences to help address barriers caused by enrollment fees, cost of textbooks, parking fees, transportation, child care, food and housing insecurity. | SP19 (ongoing) | Promise Staff | SSPC | Data which identifies barriers for Promise Students and solutions to addressing those barriers | Funding | On track - Carry forward to next year's plan
| Adopt a transcript evaluation process to help incoming students maximize units | SP19 | A&R | SSPC | ID Transcript Eval Process | TES, ESC, IT. If expanding, additional staff. | Carry forward to next year's plan. Need more detail (HS/college transcripts? Placement? For Degree/Cert/Transfer eval? Competency?)
| Streamline the matriculation process | SP19 (evaluation of process) | BPA | SSPC | New Matriculation Process | CRM, Guided Pathways (BPA), AB705 | On track - Carry forward to next year's plan
Improve pre-transfer student outcomes | Create new co-requisite English and math courses | AY 2018-19 | Math and English faculty leads | IPC | Deans |  | Complete.
| Create systems to allow all students' high school transcript data to be considered in placement | SP19 (agreement w/SUHD) | PRIE, Counseling and Assessment | SSPC/PRIE | Input Banner Data-Element for HS Transcripts | ESC, IT | Completed. Next step: Math Competency Process
| Create and align new instructional supports (e.g., embedded tutoring, a Writing Center) to support pre-transfer level students | SP19 (embedded counseling planning to begin) | Counseling | SSPC | Data showing number of embedded tutors/classes. An identified and functioning Writing Center. | Funding, staffing, ASLT coordination | Responsible Party should now be ASLT Division. No longer considering embedded counseling. Should this go back to IPC?
Expand and extend cohort bridge programs to students beyond their first year of study | Institutionalize STEM Center innovations | SP 19 (discussions/planning) | Guided Pathways | SSPC/IPC | Expanded STEM Center Innovations | Ongoing funding for Guided Pathways Leads | Not done. Needs a work group that can inform VPA of exact budget and staffing implications.
| Scale STEM Center Innovations | SP 2019 |  | SSPC/IPC |  | Align with Guided Pathways | Not done. Needs a work group that can inform VPA of exact budget and staffing implications.
| Plan for scaling First Year Experience programs for first-time students | SP19 (discussions/planning) | BPA, Promise | SSPC/IPC | FYE Program Plan | Funding, staffing | Student Voices Committee with the Promise Scholars Program are looking at this – on track. Carry forward to next year's plan.

## Progress on Goal 2
Goal 2: Community Connections | Actions to be Implemented 2018-19 | Timeline | Responsible Parties | Planning Council | Resources | Progress made in 2018-19
Increase the number of high school students successfully transitioning to Canada | Increase dual enrollment opportunities | AY 2018-19 |  | IPC |  | Not done. Discussions begun with SUHSD Board and Superintendent. Needs dedicated staff and follow up.
| Expand Middle College |  |  | IPC |  | Not done. Discussions begun with SUHSD Board and Superintendent. Needs dedicated staff and follow up.
| Utilize articulation agreements effectively |  |  | IPC |  | Not sure. This refers to HS articulation agreements
| Create new career education pathway programs | AY 2018-19 | Candice Nance and Leonor Cabrera | IPC |  | Complete. Business Program has several new and reactivated programs
| Enable earlier career exploration opportunities for high school students |  |  | IPC |  | Not done. Needs a work group aligned with Guided Pathways career exploration group.
| Scale enrollment in online course for career exploration and preparation |  | Counseling, Career Center | IPC |  | Which course? PRIE can look at enrollments
| Train faculty and staff to support student career placement |  |  | IPC/SSPC |  | On track and continuing. Change wording under Outcome from placement to guidance. Next Steps: Bob, Jeanne, Soraya, and Max will meet to talk about implementing career assessment instead of placement. Carry forward to next year's plan.
Build infrastructure for career exploration and job placement | Create an online portal for employers to connect with students and faculty |  |  | IPC/BDW |  | Not done.
| Complete mapping CE skills to industry approved digital badges and enable the link between these and student LinkedIn and other professional network sites |  |  | IPC/BDW |  | Not done
| Complete the re-branding of CE programs that is in process |  |  | APC/BDW |  | Marketing worked with BDW to create logos as well as refresh and/or create marketing material and websites for the programs in the division. In addition, Marketing partnered with BDW on a digital and social media campaign to raise awareness and increase enrollments of the BDW programs. As of now, the re-brand is complete but Marketing is available if the Division has ongoing marketing needs.
| Host alumni showcases, speaker series, and other industry events to expose students to career information and insights |  |  | APC/BDW |  | 83% complete in the current year. This is on-going
| Strengthen the CE alumni network via LinkedIn and other professional networks |  |  | APC/BDW |  | District contract with LinkedIn needs to be finalized. Programs and Career Center need to support students in creating and linking their pages. Carry forward to next year.
Host high profile signature events | Successfully launch the President's Annual Luncheon |  |  | APC |  | The first annual President’s Luncheon was launched on October 23, 2018. The event resulted in selling out the venue at 250 guests and $75,957 (total given by the SMCC Foundation) generated to support the Promise Scholars Program and other student success programs. Planning has begun for the second annual luncheon, slated for Oct. 22, 2019.
Expand and enhance 2+2 relationships with 4-year universities | Institutionalize STEM Center innovations | SP 19 (discussions/planning) | Guided Pathways | SSPC/IPC | Ongoing funding for Guided Pathways Leads | Not done. Needs a work group that can inform VPA of exact budget and staffing implications.
| Re-launch the University Center | SP19 | Dr. Mary Ho/VPSS | SSPC | Funding | Char and Mary Ho presented this at Academic Senate. Moving to Spring 20. Not on track. Carry forward to next year's plan.

## Progress on Goal 3
Goal 3: Organizational Development | Action Steps to be Implemented in 2018-19 | Timeline | Responsible Parties | Planning Council Lead | Outcomes | Resources | Progress made in 2018-19
Implement the Professional Learning Plan to support student success and promote equity. | Update provisional 2017-18 professional learning plan and develop new, 2019-2022 plan |  |  | IPC |  |  | Completed
Implement Guided Pathways-like design principles to help address equity gaps. | Clarify Academic Pathways (see Goal 1) | AY 2018-19 | Maureen Wiley | IPC |  | Guided Pathways Steering Committee - needs a work group | On-going. STEM and AD-T programs likely done by end of this academic year. Other maps to be worked on over the summer and early fall 2019.
| Facilitate Career Exploration (see Goal 2) | SP19 (offer Career 137) | Counseling, Career Center | IPC/SSPC/BPA | Providing training for Faculty and Staff to support student career guidance | Notes: Offer Career courses, Workshops (VROC), Career Workshops through the Transfer Center, Career Center, and COLTS-LC. Needs Meta Majors involvement. | On track and continuing. Next Steps: Bob, Jeanne, Soraya, and Max will meet to talk about implementing career assessment instead of placement. Carry forward to next year's plan.
| Identify and address business process barriers (see Goal 1) | SP19 | BPA, Student Voices | SSPC | Data which identies BPA barriers and proposed solutions | CRM, ongoing funding | On track. Usability experience and Student Voices. Carry forward to next year's plan.
| Align the Strategic Enrollment Plan strategies with those emerging from the Guided Pathways work | SP19 (to begin alignment) | Guided Pathways | IPC/SSPC/PRIE | Strategic Enrollment and Guided Pathways Plans | Funding | Completed
Institutionalize effective structures and best practices of HSI in order to reduce the achievement gap. | Institutionalize effective practices as part of the Guided Pathways work (see Goal 1) | SP19 (data collection) | Guided Pathways | SSPC | Implementation of new practices stemming from Guided Pathways work. | CRM, ongoing funding, participation | Apply Now button on the top of Cañada’s webpage, data collection for Student Voices and Meta Majors data collection. On track. Carry forward to next year's plan.
Update and implement Facilities Master Plan | Collaborate with the District to update Facilities Plan | SP19 (pending progress) | District Facilities | IPC/SSPC/APC | Operational buildings 1 and 23. Streamlined services in building 9 during renovation. | Building 9 signage | 83% complete in the current year. This is on-going
| Complete new buildings (1 and 23); renovate building 9 with minimum impact on students and staff |  |  | APC |  |  | Building 23 will be completed for Fall 2019. Ribbon cutting ceremony tentatively scheduled for August. Building 1 and 9 still pending.
Integrate planning and resource allocation process | Implement PBC-approved changes to program review timeline and processes |  |  | APC |  |  | Completed
Improve participatory governance process (and update Manual) | PBC Governance Work Group to review and update PGM | By May, 2019 | PBC "Fun Group with PRIE Office | PBC |  |  | Completed
Maintain accreditation status | Complete Institutional Self-Evaluation Report and identify top priority projects for Quality Focus Essay | SP19 | IPC/SSPC/APC/PRIE | IPC/SSPC/APC/PRIE | Completed ISER and QFE | Ongoing funding for Guided Pathways Leads to complete QFE objectives | Completed

## IPC Progress
Action Steps to be Implemented in 2018-19 | Timeline | Responsible Parties | Planning Council Lead | Resources | Progress made in 2018-19
Explore whether creating meta majors (interest areas) would improve student outcomes | AY 2018-19 | Maureen Wiley, Denise Erickson | IPC | Guided Pathways Meta Major Working Group | Complete. Interest Areas are being defined.
Evaluate the course schedule with respect to time-to-completion for the top 20 degree and certificate programs | AY 2018-19 |  | IPC |  | Not done
Enhance and expand distance education strategically | AY 2018-19 | Lezlee Ware | IPC | DEAC | Process for determining which courses will be offered online was documented. Enhancing the quality of on-line instruction is on-going. DEAC has recommendations that need approval.
Create new co-requisite English and math courses | AY 2018-19 | Math and English faculty leads | IPC | Deans | Complete.
Institutionalize STEM Center innovations | AY 2018-19 |  | SSPC/IPC |  | Not done. Needs a work group that can inform VPA of exact budget and staffing implications.
Scale STEM Center Innovations | AY 2018-19 |  | SSPC/IPC |  | Not done. Needs a work group that can inform VPA of exact budget and staffing implications.
Plan for scaling First Year Experience programs for first-time students | AY 2018-19 |  | SSPC/IPC |  | Not done. Needs support from a Guided Pathways work group. Faculty leads need to be identified and compensated to help lead this with a timeline.
Increase dual enrollment opportunities | AY 2018-19 |  | IPC |  | Not done. Effort stuck on hiring a Dual Enrollment Coordinator in collaboration with SUHSD.
Expand Middle College | AY 2018-19 |  | IPC |  | Not done. Discussions begun with SUHSD Board and Superintendent. Needs dedicated staff and follow up.
Utilize articulation agreements effectively |  |  | IPC |  | Not sure. This refers to HS articulation agreements
Create new career education pathway programs | AY 2018-19 | Candice Nance and Leonor Cabrera | IPC |  | Complete. Business Program has several new and reactivated programs
Enable earlier career exploration opportunities for high school students |  |  | IPC |  | Not done. Needs a work group aligned with Guided Pathways career exploration group.
Scale enrollment in online course for career exploration and preparation |  | Counseling, Career Center | IPC |  | Which course? PRIE can look at enrollments
Train faculty and staff to support student career placement |  |  | IPC/SSPC | Notes: Offer Career courses, Workshops (VROC), Career Workshops through the Transfer Center, Career Center, and COLTS-LC. Meta Majors involvement. | On track and continuing. Change wording under Outcome from placement to guidance. Next Steps: Bob, Jeanne, Soraya, and Max will meet to talk about implementing career assessment instead of placement. Carry forward to next year's plan.
Create an online portal for employers to connect with students and faculty |  |  | IPC/BDW |  | Not done.
Complete mapping CE skills to industry approved digital badges and enable the link between these and student LinkedIn and other professional network sites |  |  | IPC/BDW |  | Not done
Update provisional 2017-18 Professional Learning plan and develop new, 2019-2022 plan |  |  | IPC |  | Complete
Clarify Academic Pathways (see Goal 1) | AY 2018-19 | Maureen Wiley | IPC | Guided Pathways Steering Committee - needs a work group | On-going. STEM and AD-T programs likely done by end of this academic year. Other maps to be worked on over the summer and early fall 2019.
Facilitate Career Exploration (see Goal 2) |  |  | IPC/SSPC |  | Not done. Needs a point person on the instructional side.
Align the Strategic Enrollment Plan strategies with those emerging from the Guided Pathways work |  |  | IPC/SSPC/PRIE |  | In process. SEMP strategies aligning with GP work as defined in the ISER Quality Focus Essay.
Complete new buildings (1 and 23); renovate building 9 with minimum impact on students and staff |  |  | IPC/SSPC/APC |  | Building 23 nearly complete. Building 1 and 9, instruction not in lead role.
Complete Institutional Self-Evaluation Report and identify top priority projects for Quality Focus Essay | By April 24, 2019 | Accreditation Steering Committee with PRIE | IPC/SSPC/APC/PRIE |  | Complete

## SSPC Progress
Action Steps to be Implemented in 2018-19 | Timeline | Responsible Parties | Planning Council Lead | Outcomes | Resources | Progress made in 2018-19
Scale the Promise Program and evaluate Promise student experiences to help address barriers caused by enrollment fees, cost of textbooks, parking fees, transportation, child care, food and housing insecurity. | SP19 (ongoing) | Promise Staff | SSPC | Data which identifies barriers for Promise Students and solutions to addressing those barriers | Funding | On track - Carry forward to next year's plan
Adopt a transcript evaluation process to help incoming students maximize units | SP19 | A&R | SSPC | ID Transcript Eval Process | TES, ESC, IT. If expanding, additional staff. | Carry forward to next year's plan. Need more detail (high school/college transcripts? For placement? For Degree/Cert/Transfer eval? Competency?)
Streamline the matriculation process | SP19 (evaluation of process) | BPA | SSPC | New Matriculation Process | CRM, Guided Pathways (BPA), AB705 | On track - Carry forward to next year's plan
Create systems to allow all students' high school transcript data to be considered in placement | SP19 (agreement w/SUHD) | PRIE, Counseling and Assessment | SSPC/PRIE | Input Banner Data-Element for HS Transcripts | ESC, IT | Completed. Next step: Math Competency Process
Create and align new instructional supports (e.g., embedded tutoring, embedded counseling, a Writing Center) to support pre-transfer level students | SP19 (embedded counseling planning to begin) | Counseling | SSPC | Data showing number of embedded tutors/classes. An identified and functioning Writing Center. | Funding, staffing, ASLT coordination | Responsible Party should now be Academic Support and Learning Technologies Division. No longer considering embedded counseling. Should this go back to IPC?
Institutionalize STEM Center innovations | SP 19 (discussions/planning) | Counseling | SSPC/IPC | Fund 1 supported STEM Center Innovations | Fund 1 support | Change Responsible Party to VPI/VPSS/ASLT/VPA/Dean, Science & Technologies, Carol Rhodes and Georganne Morin. SSPC doesn’t know where we are on this.
Scale STEM Center Innovations | SP 19 (discussions/planning) | Guided Pathways | SSPC/IPC | Expanded STEM Center Innovations | Ongoing funding for Guided Pathways Leads | Same as number 6. SSPC doesn’t know where we are on this.
Plan for scaling First Year Experience programs for first-time students | SP19 (discussions/planning) | BPA, Promise | SSPC/IPC | FYE Program Plan | Funding, staffing | Student Voices Committee with the Promise Scholars Program are looking at this – on track. Carry forward to next year's plan.
Re-launch the University Center | SP19 | Dr. Mary Ho/VPSS | SSPC | Functioning University Center | Funding | Char and Mary Ho presented this at Academic Senate. Moving to Spring 20. Not on track. Carry forward to next year's plan.
Facilitate Career Exploration (see Goal 2) | SP19 (offer Career 137) | Counseling, Career Center | IPC/SSPC/BPA | Providing training for Faculty and Staff to support student career placement | Notes: Offer Career courses, Workshops (VROC), Career Workshops through the Transfer Center, Career Center, and COLTS-LC. Meta Majors involvement. | On track and continuing. Change wording under Outcome from placement to guidance. Next Steps: Bob, Jeanne, Soraya, and Max will meet to talk about implementing career assessment instead of placement. Carry forward to next year's plan.
Identify and address business process barriers (see Goal 1) | SP19 | BPA, Student Voices | SSPC | Data which identies BPA barriers and proposed solutions | CRM, ongoing funding | On track. Usability experience and Student Voices. Carry forward to next year's plan.
Align the Strategic Enrollment Plan strategies with those emerging from the Guided Pathways work | SP19 (to begin alignment) | Guided Pathways | IPC/SSPC/PRIE | Strategic Enrollment and Guided Pathways Plans | Funding | On track. Carry forward to next year's plan.
Institutionalize effective practices as part of the Guided Pathways work (see Goal 1) | SP19 (data collection) | Guided Pathways | SSPC | Implementation of new practices stemming from Guided Pathways work. | CRM, ongoing funding, participation | Apply Now button on the top of Cañada’s webpage, data collection for Student Voices and Meta Majors data collection. On track. Carry forward to next year's plan.
Complete new buildings (1 and 23); renovate building 9 with minimum impact on students and staff | SP19 (pending progress) | District Facilities | IPC/SSPC/APC | Operational buildings 1 and 23. Streamlined services in building 9 during renovation. | Building 9 signage | Should SSPC be a Responsible Party? SSPC recommends removing this from the list.
Complete Institutional Self-Evaluation Report and identify top priority projects for Quality Focus Essay | SP19 | IPC/SSPC/APC/PRIE | IPC/SSPC/APC/PRIE | Completed ISER and QFE | Ongoing funding for Guided Pathways Leads to complete QFE objectives | Completed

## APC Progress
Actions to be Implemented 2018-19 | Timeline | Responsible Parties | Planning Council | Resources | Progress made in 2018-19
Complete the re-branding of CE programs that is in process |  |  | APC/BDW |  | Marketing worked with BDW to create logos as well as refresh and/or create marketing material and websites for the programs in the division. In addition, Marketing partnered with BDW on a digital and social media campaign to raise awareness and increase enrollments of the BDW programs. As of now, the re-brand is complete but Marketing is available if the Division has ongoing marketing needs.
Host alumni showcases, speaker series, and other industry events to expose students to career information and insights |  |  | APC/BDW |  | 83% complete in the current year. This is on-going
Strengthen the CE alumni network via LinkedIn and other professional networks |  |  | APC/BDW |  | Currently exploring options with LinkedIn. On-going.
Successfully launch the President's Annual Luncheon |  |  | APC |  | The first annual President’s Luncheon was launched on October 23, 2018. The event resulted in selling out the venue at 250 guests and $75,957 (total given by the SMCC Foundation) generated to support the Promise Scholars Program and other student success programs. Planning has begun for the second annual luncheon, slated for Oct. 22, 2019.
Collaborate with the District to update Plan |  |  | APC |  | 83% complete in the current year. This is on-going
Complete new buildings (1 and 23); renovate building 9 with minimum impact on students and staff |  |  | IPC/SSPC/APC |  | Building 23 will be completed for Fall 2019. Ribbon cutting ceremony tentatively scheduled for August. Building 1 and 9 still pending.
Implement PBC-approved changes to program review timeline and processes |  |  | APC |  | 83% complete in the current year. This is on-going
Complete Institutional Self-Evaluation Report and identify top priority projects for Quality Focus Essay |  |  | IPC/SSPC/APC/PRIE |  | Currently finalizing draft with SMCCCD BOT.

## PBC Progress
Goal 3: Organizational Development | Action Steps to be Implemented in 2018-19 | Timeline | Responsible Parties | Planning Council Lead | Resources | Progress made in 2018-19
Improve participatory governance process (and update Manual) | PBC Governance Work Group to review and update | By May, 2019 | PBC "Fun Group with PRIE Office | PBC |  | Complete
Maintain accreditation status | Complete Institutional Self-Evaluation Report and identify top priority projects for Quality Focus Essay | By April 24, 2019 | Accreditation Steering Committee & ALO | PBC/PRIE |  | Complete