## Slide 1
August
November
December
February
March
April
May
October
September
January
August 1
Data Packets Available;
TracDat Open
October 11
DUE
Programs submit complete program reviews and all resource requests
November
IPC, SSPC, APC & PBC give Peer Review feedback in joint meeting
December 5
PBC prioritizes requests and presents President with prioritized list.
Oct. 30 –
Nov. 1
Position Justification Presentations
December 1
Validation concludes; PRIE & Budget Office provide information and rubric to PBC for prioritization
Mid-February
VPA returns to PBC with funding proposal
Mid-April
Budget Office notifies Programs of approved requests funded for following year
DRAFT Program Review Timeline (for 2019 and beyond)
Feb - April
VPA presents budget scenarios to PBC
Aug – Oct. 10
Departments conduct reviews
Deans provide feedback
Dec - January
President announces approved positions
(contingent on funding)
November
Academic Senate prioritizes faculty position requests
DRAFT proposal - pending approval of PBC
August Flex Day
Workshops
November 8
Deans, VPs and President submit prioritized Division or Department resource requests
Mid-January
VPA presents 3-year revenue and expense projections to PBC
Early June
VPA authorizes Divisions to make purchases
Late Jan – Early Feb
IPC Program Review Presentations
Late March
VPA & Deans discuss budget augmentation requests
October
Cabinet reviews resource requests

## Slide 2
September
November
December
February
March
April
May
October
September 15
Process Begins
November 1
Programs submit complete program reviews and all resource requests
Nov. 2 - 16
Peer Review feedback happens in IPC, SSPC, and APC
December 5
PBC prioritizes requests and presents President with prioritized list.
Oct. 30 –
Nov. 1
(Forums)
November 19
Validation concludes. PRIE & Budget Office provide complete lists and rubric to PBC for prioritization
April 15-30
VPA returns to PBC with funding proposal
May 1-15
Programs notified of what is funded for following year
October 12
New position requests due
Program Review Timeline 2018-19
Feb - April
Budget developed
Sept- Oct
Deans provide real-time feedback
January
President decides on positions after available funding announced
Nov. 2 - 16
Academic Senate prioritizes faculty position requests.
Pending approval of PBC