## Table 1
Cañada College (update 11/28/2018) Key: |  | Budgeting |  | Staffing |  | Resources |  | Planning | Evaluation
Activity | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July
Develop budget parameters, identify department budget need based upon program review | Planning Mar: Admin & Faculty
Division budgets, position control, 1310, reassignments, create draft budget | Evaluation Apr: Admin, CBO, VPI
Tentative budget submitted to District | Evaluation May: VPAS, CBO
Finalize position control | Evaluation June: VPAS, CBO
Finalize budget and submit to District | Aug: VPAS, CBO, President
Final budget approval by BOT | Budgeting Sept: President
Submit Requests for Reassignment proposal | Budgeting Oct: Faculty
Review of Requests for Reassignment | Staffing Nov: IPC
Consultations and decision | Staffing Dec: VPI
Set New position process timeline for upcoming new position process | Budgeting Sept: PBC
New position process (part of program review process) | Budgeting Oct: Divisions and Planning Councils
Announcement of approved new positions | Staffing Dec: President
Compile and report progress on plans' objectives | Aug: Plan responsible parties; Evaluation Apr: Plan responsible parties
Notify stakeholders to evaluate progress report | Budgeting Sept: PBC co- chairs
Stakeholders provide feedback on progress reports | Budgeting Sept: Stakeholders
Responsible parties revise draft program report based upon feedback from stakeholders | Budgeting Oct: Plan responsible parties
PBC approves final progress reports | Staffing Nov: PBC
Evaluation of ILO assessments and ACCJC Institutional-Set Standards | Budgeting Sept: PBC
Post program review data packets | Evaluation July: PRIE
Post SLO and PLO assessment reports | Aug: Instructional Technology
Conduct program review, submit planning objectives and resource request | Aug: Program Leads
Evaluation of program reviews and provide feedback | Budgeting Oct: Deans and Planning Councils; Staffing Nov: Planning Councils
Org managers provide feedback on program review resource requests | Staffing Nov: Deans, managers
PBC prioritizes resource requests | Staffing Dec: PBC
VPAS brings budget forecasts to PBC | Resources Jan: VPAS
VPAS brings draft budgets to PBC | Resources Feb: VPAS
Final decision on program review resource request funding | Evaluation June: VPAS
Conduct ILO Assessment | Evaluation May: PRIE
Establish governance evaluation instrument and conduct assessment | Planning Mar: PBC, PRIE
Evaluation of governance process | Evaluation Apr: IPC, SSPC, APC, Senates
Review governance evaluation and determine actions | Evaluation May: PBC