## Table 1
Cañada College Integrated Planning & Budgeting Calendar (updated 2.6.2019) | KEY: |  | Budgeting |  | Staffing |  | Resources |  | Planning |  | Evaluation
Activity | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July
Develop budget parameters, identify department budget need based upon program review | Mar: Admin & Faculty
Division budgets, position control, 1310, reassignments, create draft budget | Apr: Admin, CBO, VPI
Tentative budget submitted to District | May: VPAS, CBO
Finalize position control | June: VPAS, CBO
Finalize budget and submit to District | Aug: VPAS, CBO, President
Final budget approval by BOT | Sept: President
Submit Requests for Reassignment proposal | Oct: Faculty
Review of Requests for Reassignment | Nov: IPC
Consultations and decision | Dec: VPI
Set new position process timeline for upcoming new position process | Sept: PBC
New position process (part of program review process) | Oct: Divisions and Planning Councils
Announcement of approved new positions | Dec: President
Compile and report progress on plan objectives | Aug: Plan responsible parties; Apr: Plan responsible parties
Notify stakeholders to evaluate progress report | Sept: PBC co- chairs
Stakeholders provide feedback on progress reports | Sept: Stakeholders
Responsible parties revise draft program report based upon feedback from stakeholders | Oct: Plan responsible parties
PBC approves final progress reports | Nov: PBC
Evaluation of ILO assessments and ACCJC Institution-Set Standards | Sept: PBC
Post program review data packets | July: PRIE
Post SLO and PLO assessment reports | Aug: Instructional Technology
Conduct program review, submit planning objectives andresource requests | Aug: Program Leads
Evaluation of program reviews and provide feedback | Sept: Deans & VPs; Nov: Planning Councils
PBC prioritizes resource requests | Dec: PBC
VPAS presents 3-year revenue and expense projections | Jan: VPAS
VPAS presents budget scenarios to PBC | Mar: VPAS
Final decision on program review resource request funding | June: VPAS
Conduct ILO Assessment | May: PRIE
Establish governance evaluation instrument and conduct assessment | Mar: PBC, PRIE
Evaluation of governance process | Apr: IPC, SSPC, APC, Senates
Review governance evaluation and determine actions | Sept: PBC; May: PBC