## Slide 1: Annual Plan for implementing the College’s 5-year Education Master Plan 2023-24 Presented to the Planning & Budgeting Council on September 6, 2023

## Slide 2
Proposed Top 4 EMP Priorities for 2023-24
Create and sustain an inclusive, antiracist, and equity-minded campus culture
Expand programs and opportunities to new community members in N. Fair Oaks, Belle Haven, and East Palo Alto, especially BIPOC communities
Strengthen transfer support services to increase transfers
Reimagine how we support students’ accessing career opportunities

## Slide 3: Priority #1: Create and sustain an inclusive, antiracist, and equity-minded campus culture
  EMP Objectives for 2023-24
  2.8 Provide regular professional development that includes implicit bias and antiracism training every 2 years to all employees
  2.9 Implement a campus-wide bias incident reporting system
  2.10 Reimagine and transform college participatory governance processes and structures to address equity and antiracism in all integrated planning and resource allocation decisions
  2.11 Develop the College Cultural Center (carry forward from last year)

## Slide 4: 2.8 Provide regular, accessible, planned and intentional professional development opportunities (including implicit bias and antiracism training every two years) to all employees that sustains their personal growth and professional development over the course of employees’ careers.
Challenges?
The current HR implicit bias training needs an update
Make sure this also happens in the classroom
The training should be mandatory through HR
The training should not be mandatory. Rather, move from compliance to culture change, to engaging professional development
If we make it mandatory, are people going to get upset?
Will this be a new policing system?
This may feel overwhelming to people - it is hard to find enough time for something “extra” - especially at peak times in the academic year (Flex)
Can we offer it at off-peak times? Noon on Fridays?
Sometimes it’s the same folks engaged in this work - how can we create policy or other mechanisms to make sure everyone participates/engages
Who can facilitate an open and safe space to have hard conversations?
How can we create a culture in which we are willing to be vulnerable and accept that we need help?
We will need commitment and participation from all constituent groups, including administrators
Needed to Complete?
Need to identify staff responsible. We know from QOTL that making the training, offering it, tracking who is taking it, when they’ve done it, is a job in and of itself.
Can we include implicit bias in the QOTL or other required training?
We will need to modify the HR implicit bias training for faculty and staff. Include different case studies, different scenarios.
We have various actors in this space that still need to be coordinated (EAPC, PD Committee, Senates, Faculty Teaching & Learning Center, HR)
Who has the skills to create a curriculum? EAPC? This may require external support/experts/consultants
Can we have some kind of on-going drop in resource - so it’s not just one, long training, but also on-going dialog spaces or drop in places to ask a question
Continue Campus-wide activities for all employees such as speakers, reading a book together (in person and on-line)
Create an open space to discuss current events
Pay classified staff to do training outside of flex day.
Do we need an outside third party person to respond to incidents of bias so that we can avoid the possibility of retribution?
We have to close the loop.

## Slide 5: Who will do what on EMP 2.8?
Task Force Lead: Dean Anniqua Rana
Task Force Members (open to all): PDPC, Prof. Ellen Young, Prof. Lezlee Ware, EAPC Tri-Chair, Krystal Martinez and/or their representatives, Prof. Ray Lapuz (FLP), Roz Young (Classified Senate rep (continuing in 2023-24?), and invite others so all constituencies are represented. Consider District HR PD as well (especially the IDEAL program)
Desired Outcome: a draft college-wide professional development plan and recommendations
Timing: Report and recommendations to PBC before the end of the Fall 2023 term

## Slide 6: 2.9 Implement a campus-wide bias incident reporting system with safeguards for victims and transparent methods for addressing all reports effectively. Ensure that privacy-protected data on incidents are disseminated for analysis, policy improvements, and prevention.
Challenges?
Staffing - where does this live?
Coordinate with the District Office so we don’t duplicate efforts.
People don’t know the current process. What is it? We need to educate people.
How does this relate to the CARES reports?
How will a “bias incident reporting system” interact or integrate with existing disciplinary or evaluation systems.
Tutors, peer mentors assist in filing bias reports via the CARES reports. Adding another reporting system may be a challenge.
Trust in and support for this process may be challenging - people may fear they will be targeted as aggressors. So we will need clarity about what will happen as a result of the report, and what are potential outcomes for both the person reporting and the person/incident being reported.
We will need to address privacy concerns.
We want to avoid a hostile environment. Call in, not out.
We need closure once the issues are reported. More openness and transparency.
Needed to Complete?
We need to ensure that there isn’t retribution for reporting
We need to define a reportable bias incident
Are College personnel trained to formally investigate bias? When might a complaint process go directly to the HR complaint process.
Need clarification about reporting process, objectives, expectations.
We will need training. Perhaps a video that walks people through the process.
Just like Early Alert, we need to build trust and this may take time.
Provide support to those who may feel threatened.
Communicate that the system is for everyone, that it is identity based, and that everyone can use it and potentially benefit from it (for example, older employees might have fear of it, but they also could benefit from it)
Part-timers - we will really need to think through how to on-board them with this and how to allay any fears they might have of it.
Will it be anonymous?
Learn from the incidents reported and train the managers on how to support
Emotional support and intelligence
Use a restorative justice framework

## Slide 7: Who will do what on EMP 2.9?
Leads: Dr. Kealoha, Dean Hartman; and Mwanaisha Sims and Dr. O’KenZoe Selassie-Okpe (District)
Desired Outcomes: recommendations to EAPC and PBC
Timing: Action items to EAPC and PBC in September, 2023 regarding next steps

## Slide 8: 2.10 Reimagine and transform college participatory governance processes and structures to: (1) address equity and antiracism in all integrated planning and resource allocation decisions; (2) increase student voice in college processes, including program review; and (3) ensure classified staff have adequate time to contribute to the committees and councils on which they serve.
Challenges?
Empower EAPC to lead the antiracism and equity work
Change is hard
People feel like they don’t have time. Program Review and requesting resources is already a stressful, packed process
How can we improve/incorporate equity considerations into this process better?
Do we need equitable compensation for people who work on this?
Needed to Complete?
Open dialogue and all are regularly informed about or directly engaged in the process.
Streamline decision-making, decision-points.
How do we increase participation in general?
How do we insure representatives represent? (Senates refine # of committees, create a rotation of participation, so people experience different committees, especially including equity work)

## Slide 9: Who will do what on EMP 2.10?
Leads: EAPC Tri-Chairs, Kiran Malavade, Krystal Martinez, Michiko Kealoha
Desired Outcomes this fall: Refine EAPC priorities: PD, policies and procedures, clarify LAEP student projects
Timing: On-going

## Slide 10: 2.11 Develop the College Cultural Center (Multicultural Center) to provide timely, relevant, and intentional programming that serves the needs of the campus community in a manner that supports antiracist work at the College and more effective support for and representation of diverse racial, ethnic, and LGBTQ+ groups in the community. Include student voices on an ongoing basis to ensure the Cultural Center fosters leadership development opportunities that support understanding and interpreting various points of view that emerge from a diverse world of peoples and cultures – carry this initiative forward from last year
Challenges?
The Cultural Center does not have a solidified budget. What programs do we do and not do, how do we decide? What if we have to turn people away?
How can we engage students to use the space and what may they do in it?
How does it interact with other special programs on campus?
Make sure it is inclusive and celebrates the diverse cultures at Canada College.
Make sure that the impact of the Cultural Center is felt campus-wide, not just in the current space.
It is important for outside community partners to utilize the space.
Make sure that the Center has an online presence (social media/website)
Sometimes we see the goal, but connection may be lacking–or some may not even believe that bias or racism directly impacts people “here.”
How do we create an institutional network of sustainability and continuity over time?
Will the Cultural Center have circles or a safe space for folks to get together and say what they are going to say, “Do you want us to just listen or is this something different…”
Needed to Complete?
Ensure that equity and antiracist work and work of the Cultural Center is integrated throughout the college.
Can the Cultural Center be open in the evening as well for our evening students?
First wednesday or something, once a month brave spaces, maybe over lunch.
Could we hold courses in the Cultural Center?
Extra credit for events and things through the cultural center and community events.
Make sure all students and professors know about Umoja.

## Slide 11: Who will do what on EMP 2.11?
Lead: Dr. Michiko Kealoha
Task Force Members (open to all): Cultural Center Staff and SSPC Cultural Center Task Force
Desired Outcomes: Decision about a permanent location to College President by October 2023.

## Slide 12: Priority #2: Expand Programs and Opportunities (in NFO, BH, EPA w/emphasis on BIPOC communities)
EMP Objectives for 2023-24
1.6 New, ST, stackable certificates
1.7 Degrees and certificates available at Menlo Park and East Palo Alto
3.6 Triple the number of high school students on campus during the summer and on Saturdays during the academic year

## Slide 13: Priority #2: Expand programs and opportunities to new community members in N. Fair Oaks, Belle Haven, and East Palo Alto, especially BIPOC communities?
Challenges?
Only a few staff are actually from these communities or have familiarity with them or what the College is currently doing to serve these communities
Job Train is not that close to Belle Haven
Traffic is an obstacle and so the time classes start, even at Menlo Park, really matters.
Improve night school
Not enough transportation for students to get to campus.
Public transportation if you leave at 6 am it takes about 1 hour and ½ to get to campus. It’s expensive to get to campus from these communities
The closest High School is Menlo Atherton
Food, transportation, access to wifi are all challenges
Would a Redwood City location make more sense? It’s the center of the transit network.
How can we work better with employers to understand what kinds of programs might be most beneficial for our community members?
The lack of childcare is a big obstacle for some community members
If our transfer numbers are low, then high school students from EPA may be more likely to choose Foothill or DeAnza
Needed to Complete?
Partner with the Boys and Girls club. Have space within that community for students to work from there.
Provide a space for students to work and do their online courses. The space must have good internet.
Provide internet and technology.
Do we know if we’re offering programs that the students want? Vocational/professional certificate programs? Professional certificate?
We offer Lyft. Can we expand it? Students have to be 18 or older, which makes it challenging for middle college students.
We need financially sustainable ways to get more people to campus.
Check the UC Berkeley's intervention to help with transportation (Nimsi)
Speak with people at churches and other community centers to promote CAN and connect with the community.
Meta opened a community center. Try to partner with them to have a Cañada representation.
Contact with Meta or other partners to offer stackable certificates.
Meet with the city council to see how Cañada can better serve the Belle Haven community.
Utilize the Menlo Park center as a satellite. Not for credit classes. Collaborate with Ikea/ Target and local businesses in BH for them to get jobs so they can pursue long term goals to transfer.
Learning communities and maybe a summer bridge learning community for high school students supported by effective transportation.

## Slide 14: Who will do what on Priority #2?
Task Force Lead: Dr. Manuel Alejandro Pérez
Task Force Members (open to all – meetings will be off campus, in the community): Stephen Redmond, Mayra Arellano, Estela Garcia, Dean Bennani, Dean Sullivan-Torrez, Umoja and Puente program representatives, Silindra McRay (Chief Strategy Officer, Ravenswood USD and CAN’s newly hired professional expert (temporary contractor) with BDW/Menlo Park)
Desired Outcome (recommendations to PBC):
Continue to develop relationships and strengthen our partnerships in these communities. Boys and Girls Club MOU. Relationships with the Ravenswood USD and bringing their students to campus during the summer.
Timing: Update to PBC by the end of Fall 2023 term

## Slide 15: Priority #3: Strengthen K-16 pathways and transfer
EMP Objectives 2023-24
3.7 Fulfill the MOU with Sequoia UHSD, SF State and CSU East Bay
3.8 Strengthen transfer support services to increase transfers
3.9 Implement AB 1111 and 928

## Slide 16: Priority #3: Strengthen K-16 pathways and transfer
Challenges?
Changes to IGETC, program plans, ADT mandate: All these changes bring a lot of complexities to staff and students.
Transfer process is intimidating, demoralizing and challenging for students, especially if students end up taking unnecessary courses.
Transferring is such a complicated process, how can we better support students in understanding the process and deadlines?
Some students experience inconsistent advice from general counselors.
What are we offering for undecided students?
So many new pathway programs- dual admissions and CSU pathway programs, how do we make that more visible?
How do we get data about what dual admissions students we have on our campus?
How do we promote this program?
What about non- recent high school grads?
Handbook for first generation transfer students?
How do we partner with instructional faculty?
Needed to Complete?
Multiple Transfer Fairs to include schools other than UCs and CSUs.
Have university transfer representatives on campus.
Streamlining the transfer process
Take advantage of Transfer agreements and bring more university partnerships.
Guided Pathway and embedded counseling
Create students support groups- peer to peer support-
Invest more in more proactive counseling with dedicated counselors.
Invite Gonzalo to the community breakfast
Invite Gonzalo to meet with instructional deans.
Marketing’s “What’s Happening at Cañada Event Calendar” can start populating transfer deadlines.
Can we add evening hours for the Transfer Center?
Do we all even know about the transfer process? How can we improve what we all know about it? Faculty could help carry the message if we give it to them
The Financial Aid office could partner more with our main transfer partner students to ensure hand holding in the financial aid process. Let’s do this ASAP within our Living the Promise partners: East Bay, SF State.
We need to address the equity gap in transfer for Hispanic students.

## Slide 17: Who will do what on Priority #3?
Task Force Lead: Dr. Chialin Hsieh
Task Force Members (open to all): Max Hartman, Mary Ho, Gonzalo Arrizon, Gloria Darafshi, Ameer Thompson, James Carranza, Stephen Redmond
Desired Outcomes: Continue implementing our Living Promise MOU and review current Transfer Plan and identify areas of focus for the coming year to improve the ability of Cañada students, particularly BIPOC, low income, and first generation students to transfer to 4-year universities seamlessly in a way that closes the equity obligation the College sees in our transfer rates.
Timing: Recommendations to PBC before the end of the Fall 2023 term

## Slide 18: Priority #4: Reimagine how we support students’ accessing career opportunities
EMP Objectives
3.10 Centralize and coordinate employer relationships to scale opportunities for students
3.11 Create and expand career exploration experiences for students
3.12 Double the number of alumni connected to Cañada’s Alumni Organization by 2027 involving more of them in campus activities that strengthen the campus as a center of community life, provide career exploration for existing students, and develop new resources and connections for the College.

## Slide 19: Priority #4: Reimagine how we support students’ accessing career opportunities
Challenges?
Our two apprenticeship programs will help us learn how to do this better
How can we better coordinate employer relationships and leverage them to greater impact (into the students’ experience) - we need a vision! What could this look like?
More expertise to Career centers to support undocumented and immigrant students.
Create and develop connections to industry–with intention and direct hand-off.
How do we engage transfer students?
Challenge CRER 137 may not be included in the CalGETC pattern….
MyMajors implementation…
Need more staffing, space, sustainability
Promote from within and retain institutional knowledge.
Needed to Complete?
Encourage students to use program mapper.
Explore data to identify patterns of success for transfer and all students.
Need to be inclusive–consider undocumented students.
How do we eliminate hierarchies between career and transfer?
Every single Umoja student is a transfer student.
How do we partner with our programs?
How do we package career and transfer planning into some kind of umbrella set of messages about “what will happen next”? Maybe: “Cañada Next”?
Set up job site visits/industry visits like university visits.
Need to ask students better questions to help understand their goals (not what do you want to do, but what do you want your life to look like?)
Define what success in the area of career looks like? What metrics will we use?
How can we leverage ourselves (administrators, faculty, staff) to serve as career mentors or role models?

## Slide 20: Who will do what on Priority #4?
Task Force Lead: Dr. Karen Engel
Task Force Members (open to all): Hyla Lacefield, Max Hartman, David Gainey, Bob Haick, Interim SW Director, Career Counseling Aid (new hire), Mercedes White, Ron Andrade, EAPC representative (LAEP team (Financial Aid Office) as a resource)
Desired Outcomes: recommend to PBC on how we can better serve our students (organizational changes, programmatic changes, communication). Consider the bigger picture and make recommendations for aligning our relationships with employers to improve and scale career opportunities for students.
Timing: Report recommendations to PBC before the end of the Fall 2023 term