| Goal 1: Establish a dedicated space, resources, and program of activities for ongoing campus-wide professional learning. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Core Concept | Objective | Strategies/Activities | Timeline (completed by) | Performance Metric / Evidence of Completion /Institutionalization |
| Learning & Teaching | Identify college-wide needs for programming | Administer needs assessment | End of Spring 2017 | Assessment distributed throughout campus Data collected |
| Communication & Collaboration | Identify a space and branding for College-wide Professional Learning Program. | Determine budget Create logo and advertising Distribute information to campus | End of Fall 2017 End of Fall 2017 Ongoing beginning Fall 2017 | Budget for the 2017-18 year is set Logo is approved and materials created and distributed |
| Career & Personal Growth & Learning | Provide resources and a calendar of events | Administer needs assessment Review needs assessment data Develop budget for activities, resources, materials | End of Spring 2017 End of Spring 2017 End of Fall 2017 | Assessment distributed throughout campus Program of activities developed Resources and materials purchased, promotional materials distributed |

| Goal 2: Implement an ongoing College-wide professional learning program that engages campus constituents while creating opportunities for innovative practices that promote student success. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal | Objective | Strategies/Activities | Timeline | Performance Metric / Evidence of Completion /Institutionalization |
| Learning & Teaching | Provide employees with opportunities to learn and develop strategies that promote innovation to benefit students | Expand and coordinate communities of practice that promote learning from one another in the following areas: Faculty pedagogical discussions Tools for workplace efficiency Exploration of innovative practices Technology Social Justice and Diversity Basic Skills College Operations Leadership |  |  |
| Learning & Teaching | Expand technology skills through workshops and exploring resources | Series of technology workshops Tech Tip Tuesdays (once-a-month) Integrating technology in the classroom ELITE (new program) |  |  |
| Communication & Collaboration | Offer opportunities for inter-departmental networking in order for colleagues to explore how the college operates | Informal meet & greets Collaborative meetings (activities and projects) Conversations with colleagues Departmental sharing at meetings |  |  |
| Career & Personal Growth & Learning | Promote resources for personalized learning | California Community Colleges Professional Learning Network Grovo Skillsoft Lynda.com Workshops & courses Wellness opportunities Trainings to access professional learning funding Other resources and opportunities |  |  |
| Career & Personal Growth & Learning | Offer information on how to access Professional Development funds to further career & Personal Growth | Update webpages Offer trainings |  |  |
| Career & Personal Growth & Learning | Offer wellness resources & opportunities |  |  |  |