| Goal 1: Establish a dedicated space, resources, and program of activities for ongoing campus-wide professional learning. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Core concept | Objective | Potential Strategies/Activities | Timeline (completed by) | Performance Metric/Evidence of Completion/Institutionalization |
| Learning & Teaching | Identify college-wide needs for programming | Administer needs assessment | End of Spring 2017 | Assessment distributed throughout campus Data collected |
| Communication & Collaboration | Identify a space and branding for College-wide Professional Learning Program. | Determine budget Create logo and advertising Distribute information to campus | End of Fall 2017 End of Fall 2017 Ongoing beginning Fall 2017 | Budget for the 2017-18 year is set Logo is approved and materials created and distributed |
| Career & Personal Growth & Learning | Provide resources and a calendar of events | Administer needs assessment Review needs assessment data Develop budget for activities, resources, materials | End of Spring 2017 End of Spring 2017 End of Fall 2017 | Assessment distributed throughout campus Program of activities developed Resources and materials purchased, promotional materials distributed |

,

| Goal 2 : Implement an ongoing College-wide professional learning program that engages campus constituents while creating opportunities for innovative practices that promote student success. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Core concept | Objective | Potential Strategies/Activities | Timeline (completed by) | Performance Metric/Evidence of Completion/Institutionalization |
| Learning & Teaching | Provide employees with opportunities to learn and develop strategies that promote innovation to benefit students | Expand and coordinate communities of practice that promote learning from one another in the following areas: - Pedagogy - Workplace efficiency - Innovative practices - Technology - Social Justice & Diversity - Basic Skills - College Operations - Leadership |  |  |
| Learning & Teaching | Expand technology skills through workshops and exploring resources | - Series of technology workshops - Tech Tips - Technology in the classroom - ELITE |  |  |
| Communication & Collaboration | Offer opportunities for inter-departmental networking in order for colleagues to explore how the college operates | - Informal meet & greets - Collaborative meetings (activities & projects) - Conversations with colleagues - Departmental sharing at meetings |  |  |
| Career & Personal Growth & Learning | Promote resources for personalized learning | - California Community Colleges Professional Learning Network - Grovo - Skillsoft - Lynda.com - Workshops & courses - Wellness opportunities - Trainings to access PL funding - Other resources & opportunities |  |  |