| Goal 1: Establish a dedicated space, resources, and program of activities for ongoing campus-wide professional learning. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Core Concept | Objective | Strategies/Activities | Timeline (completed by) | Performance Metric / Evidence of Completion /Institutionalization |
| Learning & Teaching | Identify college-wide needs for programming | Administer needs assessment Research and apply models and methods for implementing PL | Beginning Fall 2017 Spring 2017 – Spring 2018 | Assessment distributed throughout campus Fall of odd years Data collected and organized |
| Communication & Collaboration | Identify a space and branding for College-wide Professional Learning Program. | Determine budget Determine branding and update space Distribute information to campus | End of Fall 2017 End of Fall 2017 Ongoing beginning Spring 2017 | Budget for the 2017-18 year is set Branding approved and space identified Calendar of activities |
| Career & Personal Growth & Learning | Provide resources and a calendar of events | Administer needs assessment Review needs assessment data Research and apply models and methods for implementing PL Coordinate PD/PL opportunities with SMCCD HR Develop budget for activities, resources, materials, personnel | Beginning Fall 2017 Beginning Fall 2017 End of Spring 2017 | Assessment distributed throughout campus Research-based program of activities developed Resources and materials purchased, promotional materials distributed, personnel identified |

| Goal 2: Implement an ongoing College-wide professional learning program that engages campus constituents while creating opportunities for innovative practices that promote student success. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Goal | Objective | Strategies/Activities | Timeline |  | Performance Metric / Evidence of Completion /Institutionalization |
| Learning & Teaching | Provide employees with opportunities to learn and develop strategies that promote innovation to benefit students | Expand and coordinate learning opportunities and communities that promote learning from one another in the following areas: Faculty pedagogical discussions Tools for workplace efficiency Exploration of innovative practices Technology Social Justice and Diversity Basic Skills College Operations Leadership Coordinate PD/PL opportunities with SMCCD HR | End of Spring 2018 |  | Increase campus response of Strongly Agree to Q 17 on the Participatory Governance Survey by 3% each year the survey is distributed On a 3-point Likert-type scale, feedback will indicate that the sessions are average to meaningful (2.5 average). Participation of a minimum of 60 different employees participating Increase Cañada participation by ____% |
| Learning & Teaching | Expand technology skills through workshops and exploring resources | Series of technology workshops Tech Tip Tuesdays (once-a-month) Integrating technology in the classroom ELITE (new program) | End of Spring 2018 |  | Increase campus response of Strongly Agree to Q 16 on the Participatory Governance Survey by 3% each year the survey is distributed On a 3-point Likert-type scale, feedback will indicate that the sessions are average to meaningful (2.5 average). Participation of a minimum of 60 different employees participating |
| Communication & Collaboration | Offer opportunities for inter-departmental networking in order for colleagues to explore how the college operates | Informal meet & greets Collaborative meetings (activities and projects) Conversations with colleagues Departmental sharing at meetings | Fall 2017 – Spring 2018 |  | One meet and greet per semester Three conversations with colleagues per semester Meet & greet and conversations with colleagues receive average to meaningful feedback on a 3-point Likert-type scale (2.5 average) |
| Career & Personal Growth & Learning | Promote resources for personalized learning | California Community Colleges Professional Learning Network Grovo Skillsoft Lynda.com Workshops & courses Wellness opportunities Trainings to access professional learning funding Other resources and opportunities |  | Spring 2018 | Increase Cañada PLN membership by 50% (from 48 to 72) Offer 2 wellness opportunities each semester Offer 1 training on accessing PL funding each semester On a 3-point Likert-type scale, feedback will indicate that the sessions are average to meaningful (2.5 average). Resource library 100 webpage hits according to Google analytics |

Last updated April 10, 2017