## Slide 1: The Excitement that Is the technology plan update
Or, “when is my computer going to be replaced”?

## Slide 2
Progress Report 2014-2015 Goal/Objective | Planning/ Discussion (25%) |  | Implementation (50%) | Ongoing (75%) | Complete (100%)
Goal 1 Technology Professional Development |  |  |  |  | 
Objective 1.1 Professional Development |  |  |  |  | 
Objective 1.2 Survey |  |  |  |  | 
Objective 1.3 New Technology |  |  |  |  | 
Goal 2 technology infrastructure |  |  |  |  | 
Objective 2.1 Determine the needs |  |  |  |  | 
Goal 3 Adaptive and Assistive technology |  |  |  |  | 
Objective 3.1 Adaptive Technology |  |  |  |  | 
Objective 3.2 Needs |  |  |  |  | 
Objective 3.3 Training |  |  |  |  | 

## Slide 3
Goals and Objectives for 2014-15
Goal 1: Optimize the use of new and existing technologies throughout the College by providing technology- related professional development resources to faculty and staff.
Or, Make sure everybody has the chance to learn how to use cool stuff

## Slide 4
Objective 1.1 The instructional designer, CIETL, and Professional Development committee will promote and increase training opportunities (internal and external) for faculty and staff to learn to use technology more effectively.
The Instructional Designer and CIETL had limited resources for engaging in new PD training opportunities.
Banner training opportunities via the district, Office 365 training, with SharePoint, one drive and degree work etc. At the College there have been specific banner trainings to departments and via flex day. Additionally Omni update training was available at Flex Day.
Hiring a full time professional development staff member who will be able to develop and support the activities. This position will incorporate instructional design, distance education, and SLO development.
The new full time position will utilize the Survey from spring 2014 was conducted and results will be used to address technology needs of the College.
Progress: implementation 50%

## Slide 5
Objective 1.2 Develop and administer instruments that survey and assess the technology training needs of faculty and staff.
This year due to administrative and personnel changes the survey for 2014-15 was not conducted. We have determined that a bi-annual survey is more realistic to our needs. The committee will be conducting this survey in the spring 2016.
Progress: ongoing 75%
Objective 1.3 Determine the necessity for new or expanded technology to ensure professional development training is provided to faculty and staff.
Office 365, one drive, Skype were offered as new and expanded training. There has been ongoing training for this throughout the year.
Progress: ongoing 75%

## Slide 6
Goal 2: To establish the technology infrastructure to continually improve the operations and services of the college.
Or, Make sure everybody has cool stuff that works
Objective 2.1 Work closely with District ITS to assess the needs of the college and determine its ability to support current and new technology.
Cycle of replacements has been created, timeline has been established. This objective has been institutionalized with the district. Timeline will be shared with all staff.
Progress: complete 100%

## Slide 7
Goal 3: Ensure that compliant and current adaptive and assistive technology is available to all students possessing any form of learning and or physical difference.
Or, give Max whatever he needs to do his job
Objective 3.1 Evaluate the present use of adaptive technology by students, faculty and staff who have a documented disability that prevents access to standard computer hardware and software.
Objective 3.2 Determine the necessity for new or expanded technology that is more likely to satisfy special learning needs.
Max and his staff have done everything (see full description online)
Progress: complete 100%

## Slide 8
Objective 3.3 Survey the need to provide training for faculty who teach hybrid and on-line courses in the use of adaptive and assistive technology.
This information was in the general survey provided to faculty and staff. The results could not be disaggregated by faculty who teach DE. The survey questions will be revised and discussed in spring 2016 for the next survey implemented in fall 2016. Results from the survey will be able to be analyzed and provide better information.
Progress: complete 100%

## Slide 9
Technology Committee Membership 2015-16
Gregory Anderson Vice President of Instruction
Nathan Staples Faculty, Science and Technology Division (co-chair)
Dean of Business, Design, & Workforce (co-chair)
Michelle Marquez Vice President Administration
Bruce Griffin SMCCD Chief Technology Officer.
Yoseph Demissie Director of Technical Support Services, Information Technology Services
Lale Yurtseven Faculty, Business Design Workforce Division
Valeria Estrada Librarian
Edith Flores, Student Services A&R
Jose Garcia Classified, Visual Communications Coordinator
Robert Haick Classified, Program Supervisor Career Center/Adjunct Faculty
Max Hartman Faculty/Director Disability Resource Center
Chialin Hsieh Dean of Planning, Research and Institutional Effectiveness
Maria Huning Classified, Program Services Coordinator Upward Bound
Ami Smith Faculty, Humanities Division
Michael Sinkewitsch IT Support Technician III, Information Technology Services
Staff Development Cordinator
Jasmine Witham District Director of Web Services
Student Representation